## RFB
Request for Bid (RFB) Check List - RFB # _____________________
| Description | Estimated Business Days | Targeted Completion Date | Date Completed
1 | Identify Standards Committee
| Is this a New or Existing Contract? ▪ If Existing, who are the current Contract Users? ▪ If New, who requested this contract? | 0 days | 2023-07-01
| Ask Section Chiefs to announce the search for Development/Standards committee members at SAPC. | 0 - 3 days | 2023-07-05
2 | Develop RFB and Supporting Docs
| Purpose and Scope | 3 - 5 days | 2023-07-12
| Bidder Qualifications | 3 - 5 days | 2023-07-19
| Mandatory Contract requirements | 3 - 5 days | 2023-07-26
| Any Special Terms and Conditions | 3 - 5 days | 2023-08-02
| Cost Sheet and other supporting documents | 3 - 5 days | 2023-08-09
| Compile list of Potential Bidders | 0 - 3 days | 2023-08-14
| Conduct Bidder Outreach | 0 - 5 days | 2023-08-21
| RFB Document and Supporting Docs Finalized | 0 days | 2023-08-21
| Peer Review | 3 - 5 days | 2023-08-28
| RFB and Supporting Documents entered into Strategic Sourcing | 1-3 days | 2023-08-31
| Section Chief Review | 10 days | 2023-09-14
| ▪ Additional Questions and Concerns Reviewed (as needed) | 3 - 5 days | 2023-09-21
| Supervisor approval to post to eSupplier | 0 - 5 days | 2023-09-28
| RFB Post date | 0 days | 2023-09-28
3 | Issue & Manage RFB
| Until Questions are due, aknowledge receipt of questions, but don't answer submitters. Compile them into Amendment Template. See Amendments and Q&A folder for template. | Same Day | 2023-09-28
| Questions Due | 5-15 days | 2023-10-19
| Meet or Email with Standards committee to answer questions received | 2-3 days | 2023-10-24
| Answers reviewed by Section Chief | 1 - 3 days | 2023-10-27
| ▪ If needed, Additional questions & concerns reviewed with Standards Committee | 0-2 days | 2023-10-26
| Post Answers to eSupplier and send Bidder Communication to announce | 0 days | 2023-10-27
| ▪ If multiple rounds of questions add two weeks and repeat last 5 steps. | 1 - 10 days | 2023-11-10
4 | Review& Award
| Due Date (Total time posted should be 4-12 weeks) |  | 2023-11-24
| Use RFB/RFP Compliance Checklist(in Bidder Submissions folder)to review responses. | 1-10 days | 2023-12-08
| Clarifications | 0 - 5 days | 2023-12-15
| Reference Checks | 0 - 5 days | 2023-12-22
| Create Cost Abstract(for single award bids, the cost abstract can be combined with the compliance abstract) | 1 - 2 days | 2023-12-26
| Complete Admin Review briefing https://doaintranet.wi.gov/SBOP/Shared%20Documents/AdminReviewBriefingTemplate.docx and send to Section Chief for review | 1 - 2 days | 2023-12-28
| Administration Review (only occurs on Thursdays) | 5 - 10 days | 2024-01-11
| Route Admin Review approval sheet for signature in Docusign. Use Docusign Template Named "Administrative Review Sign-Off". Remove any signatures for those who were not present at the meeting. | Same day | 2024-01-11
| Draft Disqualifications if relevant. See examples in Disqualification Folder. | 0 days | 2024-01-11
| Identify any records that contain proprietary or confidential information. If it exists, prepare redacted copies for records requests | 0 days | 2024-01-11
| Upon Admin Review approval, issue Notice of Intent to award and disqualifications as relevant | 0-5 days | 2024-01-18
| Protest/Appeal Period (services only), PRO-205 | 10 days | 2024-02-01
5 | Post-Award Activities
| Ensure official procurement Record file is complete. See https://doa.wi.gov/Forms/DOA-3840SPMRecordkeepingChecklist.docx | 1 day | 2024-02-02
| Negotiate any Contract terms that came up as exceptions or clarifications | 10-20 days | 2024-03-01
| Develop Contract User Guide(See template in Contract folder, subfolder Vendornet Documents) | 6 - 10 days | 2024-03-15
| Develop New Contract Analysis See https://doaintranet.wi.gov/SBOP/Shared%20Documents/ContractAnalysisForm-NewContract.docx?d=wc4a912e653564752afa9b0088ac948d9 | 7 - 10 days | 2024-03-29
| Route the Contract to Vendor(s) for signature | 5 - 10 days | 2024-04-12
| Route the Contract to DOA for signature. See https://doaintranet.wi.gov/SBOP/Shared%20Documents/eSignatureRoutingSOP.pdf | 5 - 10 days | 2024-04-26
| Post award information in STAR | 1 days | 2024-03-18
| Post Contract to Vendornet | Same Day | 2024-03-18
| Create Transactional Contract in STAR. See STAR Job Aid https://confl-star.wi.gov/display/AGNCY/Creating+a+Transactional+Contract+Job+Aid | Same Day | 2024-03-18
6 | Contract Start Date |  | 2024-03-18
| Get Contractors's review of contract user guide for completeness and accuracy. | 5 - 10 days | 2024-04-01
| Get Certificate of Insurance from Contractor. Ask them to send it to [new COI mailbox TBD] | 5 - 10 days | 2024-04-15
| Schedule Contract Kickoff Meeting with Contractor, Fill out Contract Kickoff sheet. See Contract folder, subfolder Contractor Communications and Performance | 5 - 10 days | 2024-04-29
| Schedule monthly or quarterly meetings with Contractor, as applicable. | 5 - 10 days | 2024-05-13
Formulas:
Targeted Completion Date = WORKDAY([Targeted Completion Date, row above],3)