## Sheet1
Request for Bid (RFB) Check List - RFB # _____________________
| Description | Handled By | Estimated Business Days | Targeted Completion Date | Completed | Date Completed
1 | Identify Need
| - Is this a New or Existing Procurement? ▪ If existing what is the current contract number? | Agency | 0 days | 2021-04-01 | New □ Existing □
| - Is this a software purchase? If yes, can it be purchased using the Value-Added Reseller (VAR) contract? | Agency | 0 - 3 days | 2021-04-06 | Yes □ No □
| - If it’s not a software purchase, is there an existing contract that can be used? |  |  |  | Yes □ No □
| - Decide if the procurement is a Commodity or a Service AND create a timeline based on the target contract start date. | Agency/CAPS | 0 days | 2021-04-06 | Service □ Commodity □
2 | Develop RFB
| Procurement Plan: Services Only, PRO-201 |  |  |  | Yes □ No □
| - Complete Procurement Plan and send, via email, to Procurement Specialist | Agency | 0 - 4 days | 2021-04-12 | □
| - Sends completed Procurement Plan to Bureau of Procurement Office | CAPS | 0 days | 2021-04-12 | □
| - Receives approved or denied Procurement Plan | CAPS | 7 - 10 days | 2021-04-26 | □
| Cost Benefit Analysis (CBA): Services Only, PRO-205 |  |  |  | Yes □ No □
| - Complete CBA and send, via email, to Procurement Specialist | Agency | 0 - 5 days | 2021-04-26 | □
| - Sends completed CBA to Bureau of Procurement Office | CAPS | 0 days | 2021-04-26 | □
| - Tracking Number | CAPS | 0 days | 2021-04-26 | □
Request for Bid Document and Cost Sheet Preparation
| - Purpose and Scope | Agency | 10 - 15 days | 2021-05-17 | □
- Bidder Qualifications
| - Mandatory Specifications (Technical Requirements, Performance and Support Requirements, etc.) |  |  |  | □
| - Any Special Terms and Conditions |  |  |  | □
| - Cost Sheet |  |  |  | □
| - Compile list of Potential Bidders | Agency | 0 - 3 days | 2021-05-20 | □
| - Bidder Outreach | CAPS | 0 - 5 days | 2021-05-27 | □
| - RFB Document and Cost Sheet entered into Strategic Sourcing | CAPS | 12 - 15 days | 2021-06-17 | □
| - Collaboration/Review of Procurement Specialist questions and concerns | Agency/CAPS | 10 - 12 days | 2021-07-05 | □
| - RFB Document and Cost Sheet Finalized | Agency/CAPS | 0 days | 2021-07-05 | □
| - Peer Review | CAPS | 3 - 5 days | 2021-07-12 | □
| - RFB Section Chief Review | CAPS | 10 days | 2021-07-26 | □
| ▪ Additional Questions and Concerns Reviewed (as needed) |  | 3 - 5 days | 2021-08-02 | □
| - Agency approval to post to eSupplier | Agency | 0 - 5 days | 2021-08-09 | □
| - RFB Posting to eSupplier (total time posted 4 - 8 weeks) | CAPS | 0 days | 2021-08-09 | □
3 | Issue & Manage RFB
| - Questions Due | CAPS | 5 day | 2021-08-16 | □
| - Answer Questions received | Agency | 4 - 5 days | 2021-08-20 | □
| - Answers reviewed by Section Chief Additional questions & concerns reviewed (as needed) | CAPS | 1 - 2 days | 2021-08-24 | □
| - Post to eSupplier/Bidder Communication | CAPS | 0 days | 2021-08-24 | □
| ▪ If multiple rounds of questions, repeat a) - d) | CAPS | 1 - 10 days | 2021-08-24 | Yes □ No □
4 | Review& Award
| Due Date: Review for completeness |  |  | 2021-08-31
| - Do Bidders meet all Bidder Qualifications? | CAPS | 1 day | 2021-09-01 | □
| - Do Bidders meet all Mandatory Requirements? |  |  |  | □
| - Do Bidders provide all required documentation (DOA forms, supporting documents, etc.)? |  |  |  | □
| - Do Bidders provide a completed Cost Sheet? |  |  |  | □
| - Do Bidders take any exceptions to the Special Terms and Conditions? |  |  |  | □
| - Clarifications | CAPS | 0 - 5 days | 2021-09-08 | □
| - Reference Checks | Agency | 0 - 5 days | 2021-09-15 | □
Cost Evaluation
| - Cost Abstract created | CAPS | 1 - 2 days | 2021-09-17 | □
Eligible/Ineligibility Status Checks
| - Certification for Collection of Sales and Use Tax Ineligible Directory | CAPS | 0 days | 2021-09-17 | □
| - WI Office of Contract Compliance Ineligible Vendor Directory | CAPS | 0 days | 2021-09-17 | □
| - Federal Debarment List—if using Federal Funds | CAPS | 0 days | 2021-09-17 | □
| Administration Review (only occurs on Thursdays) | CAPS | 5 - 10 days | 2021-10-01 | □
| - Agency notified of Admin Review approval and Notice of Intent to award | CAPS | 0 days | 2021-10-01 | □
| ▪ Award, Non-Award, and Disqualification Letters sent to vendor(s) |  |  | 2021-10-01 | □
| - Document information identified as proprietary or confidential | CAPS | 0 days | 2021-10-01 | □
| - Protest/Appeal Period (services only), PRO-205 | Agency | 10 days | 2021-10-15 | □
5 | Post-Award Activities
| - Contract Number/Transactional Contract | CAPS | 1 day | 2021-10-18 | □
| - Ensure official procurement file is complete | CAPS | 1 day | 2021-10-19 | □
| - Post award information in STAR | CAPS | 0 days | 2021-10-19 | □
| - Contract | Agency | 15 days | 2021-11-09 | □
Formulas:
Targeted Completion Date = WORKDAY([Targeted Completion Date, row above],3)