## Year-End
State of Wisconsin
FY2026 Year-End Closing and Reconciliation Task List
SCO Task
Agency Task
No. | Entity | Task | Task Details | Due | Module or Fiscal Year closing
1 | SCO | Continuing KK to GL reconciliation of expenditures, adjusting entries made. | This is an ongoing task. Any differences as of 6/30 will be adjusted by the SCO by 7/2. The SCO will continue to run reconciliations through 8/7 making sure all necessary adjustments are made. Agencies will be notified of all adjusting entries as they are made. NOTE: FY 2026 will be closed for Non-Project agencies on Friday, 7/31. So, that Friday, 7/31/26, KK to GL reconciliation should be the final substantive reconciliation before closing. The SCO will make a final check of all Non-Project agencies on 8/4/26 to ensure that no additional issues were introduced that week. For Project Agencies, the final reconciliation will be 8/5, with a final check on 8/7. | ongoing
2 | SCO | Continuing analysis and reconciliation of Collected Revenue (CC_REV_COL) ledger. | This is an ongoing task. Any differences as of 06/30/2026 will be adjusted by SCO by 07/02/2026. Subsequently, the SCO will continue to run reconciliations through 8/7 making sure all necessary adjustments are made. NOTE: FY 2026 will be closed for Non-Project agencies on Friday, 7/31. So, Friday 07/24, Collected Revenue reconciliation should be the final substantive reconciliation before closing. The SCO will make a final check of all Non-Project agencies on 7/31 to ensure that no additional issues were introduced that week. For Project Agencies, the final reconciliation will be 8/5, with a final check on 8/11. | ongoing
3 | Agency | Process all open vouchers, journals, interunit transactions as June 30th (see monthly SCO checklist). | See Section 18-01 of the Wisconsin Accounting Manual | 2026-07-07
4 | Agency | Review trial balance and flag accounts that appear incorrect. Created inventory of all clearing appropriations that need adjusting/correcting entries. | See Section 18-01 of the Wisconsin Accounting Manual | 2026-07-07
5 | Agency | Process outstanding FY 2026 June and prior Interunit billing transactions (see inter-unit billing job aid) | See Popular Job Aids | 2026-07-10
6 | Agency | Procurement YEC Pre-Roll Tasks Completed | See Procurement YEC Work Center in STAR | 2026-07-16
7 | Agency | Complete year-end Travel Expense Tasks | See FY 2026 Travel Expense Closing Instructions | 2026-07-16
8 | Agency | Complete year-end Accounts Payable Tasks | See FY 2026 Accounts Payable Closing Instructions | 2026-07-16
9 | SCO | Final Pension Obligation Bond charges recorded for FY 2026. |  | 2026-07-17
10 | SCO | FSA and HSA Administrative Fees Allocated by the SCO to appropriation 97100. |  | 2026-07-17
11 | SCO | AP Closed for FY 2026 |  | 2026-07-17
12 | DOA | FY 2026 Purchase Order Roll |  | 7/18-7/19
13 | SCO | Pay Plan Supplement Budget Journals Entered into STAR. | The completion of this task will depend on approvals from the Joint Committee on Finance and the State Budget Office. | 2026-07-22
14 | SCO | Completes final reconciliation of the AP Control Account (2000000). |  | 2026-07-24
15 | SCO | Completes final reconciliation of the AR Control Account (1351000). |  | 2026-07-24
16 | SCO | Completes final reconciliation of HR Accounting Line table in HCM with GL Payroll Journals. Differences are verified to pay period corrections, and detailed worksheet sent to those agencies with differences. |  | 2026-07-24
17 | Agency | Complete final reconciliation of expenses. | See Checklist in Section 18-01 WI Acctg Manual | 2026-07-24
18 | Agency | Complete final reconciliation of Benefits. | See Wisconsin Reconciliation Manual | 2026-07-24
19 | Agency | Process any remaining FY 2026 Interunit Transactions. | See Popular Job Aids | 2026-07-24
20 | Agency | Post all GL Journals that have been budget checked. | Query: WI_GL_JRNL_NOT_POSTED | 2026-07-24
21 | Agency | Complete NSF Fee Revenue entries in account 5999000. | Update pending to the Wisconsin Accounting Manual (see WiSMART Accounting Manual Section VI-7 for basic entries). | 2026-07-24
22 | SCO | SCO processes NSF revenue entries to transfer revenues from account 5999000 to the DOA GPR earned approriation. | Update pending to the Wisconsin Accounting Manual. | 2026-07-24
23 | Agency | Completes correcting/adjusting entries to all clearing appropriations - all balances cleared. | Job Aid: Enter and Process Journals | 2026-07-24
24 | SCO | Life insurance expenditures reclassified to prepaids for pay period 12A. | SCO processes reclassification entries for life insurance only, as these amounts are not paid until July. | 2026-07-30
25 | SCO | Life insurance expenditures reclassified to prepaids for pay period 13B. | SCO processes reclassification entries for life insurance only, as these amounts are not paid until July. | 2026-07-30
26 | SCO | Life insurance expenditures reclassified to prepaids for pay period 14A. | SCO processes entries to move life AND health expenditures from FY 2026 to FY 2026 as this pay period is paid in July. | 2026-07-30
27 | Agency | Complete Non-statutory transfers/lapses | Instructions sent out from SBO to agencies; due dates are 7/24 for non-project agencies and 7/31 for project agencies
28 | SCO | SCO processes surplus property entries to transfer revenues from account 5950000 to the Budget Stabilization Fund |  | 2026-07-31
29 | SCO | FY 2026 Closed for all Non-Project Agencies |  | 2026-07-31
30 | Agency | Final Form 78 Certifications for Non-Project Agencies | Form 78 User Guide | 2026-08-04
31 | Agency | Complete final reconciliation of Project Costing. | See Checklist in Section 18-01 WI Acctg Manual | 2026-08-05
32 | SCO | Project Costing closed for Project Agencies |  | 2026-08-05
33 | SCO | BI closed for Project Agencies |  | 2026-08-06
34 | SCO | AR closed for Project Agencies |  | 2026-08-07
35 | SCO | FY 2026 Closed for all agencies except for DOR. |  | 2026-08-07
36 | Agency | PO increase justification worksheets due to the SCO (templates to be distributed by 7/22). |  | 2026-08-07
37 | Agency | Final Form 78 Certifications for Project Agencies |  | 2026-08-11