## Year-End
State of Wisconsin
Year-End Closing and Reconciliation Task List
Updated 8/4/2016
No. | Task | Task Details | Due Date | Compl Date
1 | Process all open vouchers, journals, interunit transactions as necessary (see pre-closing checklist). | Section 18-01 WI Acctg Manual | 2016-06-30
2 | Review trial balance and flag accounts that appear incorrect. | Reconciliation - Approach to Trial Balance Validation | 2016-07-11
3 | Process outstanding FY 2016 June and prior Interunit transactions | See Interunit Job Aids | 2016-07-15
4 | Review open PO's and close those that do not need to be carried into FY 2017. | Query: WI_PO_ENC_ALL_OPEN_PO | 2016-07-15
5 | Create inventory of clearing appropriations that need adjusting/correcting entries. | Review trial balance for 9**** appns | 2016-07-15
6 | Perform initial reconciliation of Commitment Control to the Actuals Ledger - submit adjustments to DOA. | Reconciliation Manual - Commitment Control | 2016-07-22
7 | Perform initial reconciliation of the AP Control Account (2000000) - submit adjustments to DOA. | Reconciliation Manual - AP Control Account | 2016-07-22
8 | Perform initial reconciliation of the AR Control Account (1351000) - submit adjustments to DOA. | Reconciliation Manual - AR Control Account | 2016-07-22
9 | Perform initial reconciliation of expenses. | See Checklist in Section 18-01 WI Acctg Manual | 2016-07-22
10 | Perform initial reconciliation of Project Costing. | Reconciliation Manual - Project Costing | 2016-07-22
11 | Perform initial reconciliation of HCM accounting. | Reconciliation Manual - HCM Accounting | 2016-07-22
12 | Perform initial reconciliation of Benefits. | Reconciliation Manual - Benefits | 2016-07-22
13 | Complete final AP and Expense processing for FY 2016. | See AP and Expense Job Aids | 2016-07-22
14 | Submit Reconciliation Status Report to the SCO. | Email: DOASCOYearEnd@wi.gov | 2016-07-25
15 | Process any remaining FY 2016 Interunit Transactions. | See Interunit Job Aids | 2016-07-27
16 | Post all GL Journals that have been budget checked. | Query: WI_GL_JRNL_NOT_POSTED | 2016-07-27
17 | Perform final reconciliation of Commitment Control to the Actuals Ledger - submit adjustments to DOA | Reconciliation Manual - Commitment Control | 2016-08-05
18 | Perform final reconciliation of the AP Control Account (2000000) - submit adjustments to DOA. | Reconciliation Manual - AP Control Account | 2016-08-05
19 | Perform final reconciliation of the AR Control Account (1351000) - submit adjustments to DOA. | Reconciliation Manual - AR Control Account | 2016-08-05
20 | Perform final reconciliation of expenses. | See Checklist in Section 18-01 WI Acctg Manual | 2016-08-05
21 | Perform final reconciliation of Project Costing. | Reconciliation Manual - Project Costing | 2016-08-05
22 | Perform final reconciliation of HCM accounting. | Reconciliation Manual - HCM Accounting | 2016-08-05
23 | Perform final reconciliation of Benefits. | Reconciliation Manual - Benefits | 2016-08-05
24 | Complete correcting/adjusting entries to all clearing appropriations - all balances cleared. | Job Aid: Enter and Process Journals | 2016-08-05
25 | Form 78's Released | Form 78 Job Aid Pending | 2016-08-08
26 | Final correcting/adjusting entries made to FY 2016 Period 12 in STAR. | Job Aid: Enter and Process Journals | 2016-08-12
27 | Form 78 Certifications Due. | Form 78 Job Aid Pending | 2016-08-19