## Sheet1
PROJECT NAME: |  |  |  |  | TYPE OF SUBMITTAL CODE |  |  |  |  | ACTIONS
PROJECT NO: |  |  |  |  | AT = Attic Stock |  | SA = Samples |  |  |  | R | = Reviewed
CONTRACTORS: |  |  |  |  | OM = Oper/Maint. |  | SD = Shop Drawings |  |  |  | C | = Reviewed w/ comments
[5 empty] | PD = Product Data |  | TC = Tests/Certif. |  |  |  | X | = Rejected
[5 empty] | RP = Reports |  | WR = Warranty
Date Contractor will Submit | Date Rec'd | Spec Section | Submittal Type | Title | Manufacturer/ Supplier/Contractor | Required to meet BABA Act Compliance | No. Rec'd | Referred To | Date Sent | No. Sent | Date Ret'd | Action | Date Ret'd to Contractor | Remarks
|  | 01 00 00 |  | DIVISION 01 - GENERAL REQUIREMENTS
|  | GC Art #8 |  | Prof of permits, licenses and approvals
mm/dd/yy |  | GC Art #13 |  | Contractor - 60 day initial schedule | [9 empty] | Due 14 days from NTP
|  | GC Art #13 |  | Contractor - full project schedule
|  | GC Art #15 |  | Qualtiy Control Plan
|  | GC Art #19 |  | Work Reports
|  | GC Art #23 |  | Contractor Written Req - Subst Completion-Insp
|  | GR Art #33 |  | Operation and Maintenance Manuals and Instructions
|  | GR Art #36 |  | Erosion Control and Storm Water Management
|  | GR Art #39 |  | Guarantee Documents / Individual Divisions
|  | GR Art #40 |  | Record Documents - marked up as-builts
|  | 01 74 19 |  | Construction Waste Management (CWM) Plan | [9 empty] | GR Art #38
Summary of CWM Progress Reports
Summary of CWM Final Documentation
|  | 01 91 00 |  | COMMISSIONING - SEE Cx LOG
|  | 02 00 00 |  | DIVISION 02 - EXISTING CONDITIONS
|  | 03 00 00 |  | DIVISION 03 - CONCRETE
|  | 04 00 00 |  | DIVISION 04 - MASONRY
|  | 05 00 00 |  | DIVISION 05 - METALS
|  | 06 00 00 |  | DIVISION 06 - WOOD, PLASTIC & COMPOSITES
|  | 07 00 00 |  | DIVISION 07 - THERMAL & MOIST. PROTECT.
|  | 08 00 00 |  | DIVISION 08 - OPENINGS
|  | 09 00 00 |  | DIVISION 09 - FINISHES
|  | 10 00 00 |  | DIVISION 10 - SPECIALTIES
|  | 11 00 00 |  | DIVISION 11 - EQUIPMENT
|  | 12 00 00 |  | DIVISION 12 - FURNISHINGS
|  | 13 00 00 |  | DIVISION 13 - SPECIAL CONSTRUCTION
|  | 14 00 00 |  | DIVISION 14 - CONVEYING EQUIPMENT
|  | 21 00 00 |  | DIVISION 21 - FIRE SUPPRESSION
|  | 22 00 00 |  | DIVISION 22 - PLUMBING
|  | 23 00 00 |  | DIVISION 23- HVAC
|  | 26 00 00 |  | DIVISION 26 - ELECTRICAL
|  | 27 00 00 |  | DIVISION 27 - COMMUNICATIONS
|  | 28 00 00 |  | DIVISION 28 - ELECT. SAFETY & SECURITY
` |  | 31 00 00 |  | DIVISION 31 - EARTHWORK
` |  | 32 00 00 |  | DIVISION 32 - EXTERIOR IMPROVEMENTS
` |  | 33 00 00 |  | DIVISION 33 - UTILITIES
*** END OF DOCUMENT ***
` |  |  |  | DIVISION