## Year-End
State of Wisconsin
FY 2017 Year-End Closing and Reconciliation Task List
Updated: 08/7/2017
No. | Entity | Task | Task Details | Due Date | Compl Date
1 | SCO | Completes initial KK to GL recon and processes adjusting budget journals at the appropriation level. |  | 2017-06-15 | 3/31 reconciling entries entered by mid-June. Ongoing.
2 | Agency | Complete review of Expense Reports in tasks #1 - #3 of year-end process (ER's that have a budget linked to them). | http://doa.wi.gov/Divisions/Budget-and-Finance/DEBF-Information-for-State-Agencies/FY-2017-Closing/ | 2017-06-29 |  | Added 6/12
3 | Agency | Process all open vouchers, journals, interunit transactions as June 30th (see monthly pre-closing checklist). | Section 18-01 WI Acctg Manual | 2017-07-06
4 | Agency | Review trial balance and flag accounts that appear incorrect. | Reconciliation - Approach to Trial Balance Validation | 2017-07-10
5 | SCO | Final Pension Obligation Bond charges determined for FY 2017. |  | 2017-07-14 | 2017-07-13 | Added 6/21
6 | SCO | ERA and HSA Administrative Fees Allocated by the SCO to appropriation 971 |  | 2017-07-14 | 2017-07-24 | Added 7/11
7 | Agency | Process outstanding FY 2017 June and prior Interunit billing transactions (see inter-unit billing job aid) | See Popular Job Aids | 2017-07-14
8 | Agency | Review open PO's and close those that do not need to be carried into FY 2017. | Query: WI_PO_ENC_ALL_OPEN_PO | Initial: 7/14/2017 Final: 7/21/2017
9 | Agency | Create inventory of clearing appropriations that need adjusting/correcting entries. | Review trial balance for 9**** appns | 2017-07-14
10 | Agency | All remaining Expense Reports Reviewed - tasks #4 - #6 of year-end process. | http://doa.wi.gov/Divisions/Budget-and-Finance/DEBF-Information-for-State-Agencies/FY-2017-Closing/ | 2017-07-20 |  | Added 6/12
11 | SCO | Life Insurance expenditure prepaid reclassification entries completed. |  | 2017-07-21 | 2017-07-24 | Added 6/21
12 | SCO | Completes initial reconciliation of the AP Control Account (2000000). |  | 2017-07-21 | in process
13 | SCO | Completes initial reconciliation of the AR Control Account (1351000). |  | 2017-07-21 | in process
14 | SCO | Completes final reconciliation of HR Accounting Line table in HCM with GL Payroll Journals. Differences are verified to pay period corrections, and detailed worksheet sent to those agencies with differences. |  | 2017-07-21 | in process
15 | Agency | Perform initial reconciliation of expenses. | See Checklist in Section 18-01 WI Acctg Manual | 2017-07-21
16 | Agency | Perform initial reconciliation of Project Costing. | Reconciliation Manual - Project Costing | 2017-07-21
17 | Agency | Perform initial reconciliation of HCM accounting. | Reconciliation Manual - HCM Accounting | 2017-07-21
18 | Agency | Perform initial reconciliation of Benefits. | Reconciliation Manual - Benefits | 2017-07-21
19 | Agency | Completes final AP and Expense processing for FY 2017. | See AP and Expense Job Aids | 2017-07-21
20 | Agency | Submit July 21st Reconciliation Status Report to the SCO. | Email: DOASCOYearEnd@wi.gov | 2017-07-24
21 | SCO | PO justification worksheets forwarded to the agencies (for new and increased FY 2017 PO's entered after 5/31/2017 - and for any remaining FY 2016 and older encumbrances carried forward into FY 2018). |  | 2017-07-24 |  | Added 6/21
22 | Agency | Initial Collected Revenue Analysis completed - adjustments forwarded to the SCO. | See Instructions for Collected Revenue Analysis | 2017-07-26 |  | Modified 7/11
23 | SCO | All Collected Revenue adjustments processed by the SCO |  | 2017-07-28 |  | Added 6/22
24 | Agency | Process any remaining FY 2017 Interunit Transactions. | See Popular Job Aids | 2017-07-28
25 | Agency | AM updated for all Adds, Retirements and Adjustments - Tier 1 Agencies |  | 2017-07-28 |  | Added 7/18
26 | SCO | Run final depreciation job for FY 2017 and close period 12 in AM for Tier 1 Agencies |  | 2017-07-28 |  | Added 7/18
27 | Agency | Post all GL Journals that have been budget checked. | Query: WI_GL_JRNL_NOT_POSTED | 2017-07-28
28 | SCO | Period 12 closed and Period 996 opened for Non-Project Agencies (except DOR) |  | 2017-07-28 |  | Added 6/19
29 | Agency | Agencies complete NSF Fee Revenue entries to their 99300 appropriation. | Update pending to the Wisconsin Accounting Manual (see WiSMART Accounting Manual Section VI-7 for basic entries). | 2017-07-28 |  | Added 7/5
30 | Agency | PO justification worksheets due to the SCO. | http://www.doa.state.wi.us/Documents/DEBF/Information%20for%20State%20Agencies/Wisconsin%20Accounting%20Manual/04%20ENCUMBRANCES/04-03%20Carryover%20of%20Encumbrances.pdf | 2017-07-31 |  | Added 6/21
31 | SCO | Completes final KK to GL recon and processes adjusting budget journals at the appropriation level. |  | 2017-08-04
32 | Agency | Final Collected Revenue analysis completed - final adjustment templates submitted to the SCO. |  | 2017-08-04 |  | Added 6/22
33 | SCO | Perform final reconciliation of the AP Control Account (2000000). |  | 2017-08-04
34 | SCO | Perform final reconciliation of the AR Control Account (1351000). |  | 2017-08-04
35 | Agency | Perform final reconciliation of expenses. | See Checklist in Section 18-01 WI Acctg Manual | 2017-08-04
36 | Agency | Perform final reconciliation of Project Costing. | Reconciliation Manual - Project Costing | 2017-08-04
37 | Agency | Perform final reconciliation of HCM accounting. | Reconciliation Manual - HCM Accounting | 2017-08-04
38 | Agency | Perform final reconciliation of Benefits. | Reconciliation Manual - Benefits | 2017-08-04
39 | Agency | Completes correcting/adjusting entries to all clearing appropriations - all balances cleared. | Job Aid: Enter and Process Journals | 2017-08-04
40 | SCO | SCO processes entry to sweep the 99300 appropriations and move NSF revenues to DOA GPR-Earned appropriation. | Update pending to the Wisconsin Accounting Manual. | 2017-08-04 |  | Added 7/5
41 | SCO | SCO processes surplus property entries to transfer revenues from account 5950000 to the Budget Stabilization Fund |  | 2017-08-04 |  | Added 7/24
42 | SCO | Final Collected Revenue adjustments entered by the SCO (based on adjustment templates submitted by the agencies). |  | 2017-08-11 |  | Added 6/22
43 | SCO | Project Costing Closed for Project Agencies |  | 2017-08-16 |  | Added 6/19, Modified 8/7
44 | SCO | AR and BI closed for Project Agencies |  | 2017-08-18 |  | Added 6/19, Modified 8/7
45 | SCO | Period 12 GL closed and Period 996 opened for Project Agencies |  | 2017-08-18 |  | Added 6/19, Modified 8/7
46 | Agency | Final correcting/adjusting entries made. | Job Aid: Enter and Process Journals | 2017-08-18 |  | Modified 8/7
47 | Agency | Form 78 Certifications Due. | Form 78 User Guide | 8/12/2017 - 8/18/2017
48 | Agency | AM updated for all Adds, Retirements and Adjustments - Tier 2 Agencies |  | 2017-08-18 |  | Added 7/18
49 | SCO | Run final depreciation job for FY 2017 and close period 12 in AM for Tier 2 Agencies |  | 2017-08-18 |  | Added 7/18
50 | SCO | FY 2017 Closed in STAR (All Subsystems and GL Periods - except Asset Management) |  | 2017-08-18 |  | Added 6/19